## Design Inspection
Product | Categories Module
Date | 2017-09-15
Author | Sugarbois
Moderator | Ivan Chan
Inspectors | Rei Orikata, Tim Poozhikala
Recorder | Ronak Bharad
Defect # | Description | Severity | How corrected
1 | CategoriesUI should be in one file using vue.js, not in 3 files of html, css, and js | 3 | CategoriesUI is now all in one file
2 | Dropdown Module does not contain a component to add a category | 1 | Dropdown Module now contains an AddCategory component
3 | Dropdown Module does not contain a subcategory dropdown | 1 | Dropdown module now contains a SubCatDrop component
Product | Add a question Module
Date | 2017-09-17
Author | Sugarbois
Moderator | Rei Orikata
Inspectors | Ivan Chan, Tim Poozhikala
Recorder | Ronak Bharad
Defect # | Description | Severity | How corrected
1 | AddaQuestion should be in one file using vue.js, not in 3 files of html, css, and js | 3 | AddaQuestion is now all in one file
2 | AddaQuestion module does not have component to change type of answer | 1 | AddaQuestion now contains a T/F and MC component
3 | AddaQuestion module does not have component to choose the category of adding the question to | 1 | AddaQuestion now contains the Dropdown component for categories
Product | Login Module
Date | 2017-09-16
Author | Sugarbois
Moderator | Tim Poozhikala
Inspectors | Rei Orikata, Ivan Chan
Recorder | Ronak Bharad
Defect # | Description | Severity | How corrected
1 | Login module does not have a component to register a user | 1 | Login now contains a Register Component
2 | Login module does not have a component to check for userID and the password | 1 | Login now contains a component to check the ID and password
3 | Login module does not have component to secure passwords and emails from being hacked | 2 | Login now contains an encrypt component
Product | Profile Module
Date | 2017-09-15
Author | Sugarbois
Moderator | Ivan Chan
Inspectors | Ronak Bharad, Rei Orikata
Recorder | Tim Poozhikala
Defect # | Description | Severity | How corrected
1 | Profile module should be in one file using vue.js, not in 3 files of html, css, and js | 3 | Profile module is now all in one file
2 | Profile does not have a component to check the user's wrong questions | 2 | Profile module now has WrongQ component
3 | Profile does not have a component to check the ranking of the user | 2 | Profile module now has Ranking component
Product | Settings Module
Date | 2017-09-20
Author | Sugarbois
Moderator | Ronak Bharad
Inspectors | Rei Orikata, Tim Poozhikala
Recorder | Ivan Chan
Defect # | Description | Severity | How corrected
1 | Settings module does not have a component to change grid size | 2 | Settings module now has GridSize component
2 | Settings module does not have a component to change question timer | 2 | Settings module now contains a Timer component

## Code Inspection
Product | Categories module
Date | 2017-09-15
Author | Sugarbois
Moderator | Ronak Bharad
Inspectors | Rei Orikata, Ivan Chan
Recorder | Timothy Poozhikala
Defect # | Description | Severity | How Corrected
1 | After clicking the category dropdown box, it shows all categories the website currently has. It might duplicate if somebody tries to add the new category with same as one that already exists. | 3 | Check the name inside the database each time when the new category field is added.
2 | After clicking the subcategory dropdown box, it shows all categories the website currently has. It might duplicate if somebody tries to add the new category with same as the one already exists. | 3 | Check the name inside the database each time when the new subcategory field is added.
Product | Settings Module
Date | 2017-09-20
Author | Sugarbois
Moderator | Timothy Poozhikala
Inspectors | Ronak Bharad, Rei Orikata
Recorder | Ivan Chan
Defect # | Description | Severity | How Corrected
1 | After building the page with multiple boxes of rules it should adjust to the size of the browser, which wasn't happening, it was just removing that part of the boxes | 2 | The size was not set dynamically. It was set to a size and if the webpage gets smaller than that it was removed. We fixed it by making size dynamic.
2 | The allignment of the title and all the rules weren't in the center and all the formating looked weird. The stuff that was supposed to underlined werent underlined. | 2 | The CSS code was fixed giving proper access as well as making it dynamically under the subject and not static on the screen.
3 | After changing the setting of the number of connects the game is supposed to end declare the winner after the new number has been achieved | 1 | Fixed algorithm to flag that it has reached the number of connect and game needs to end
Product | Login and Signin Module
Date | 2017-09-16
Author | Sugarbois
Moderator | Timothy Poozhikala
Inspectors | Rei Orikata, Ivan Chan
Recorder | Ronak Bharad
Defect # | Description | Severity | How Corrected
1 | After filling out the infomation, it will be sent to the database. However, even if the the information is blank, it would still store the information to the database. | 2 | We added the code to check if the infomation is blank or not.
2 | When we try to login, it will generate a json web token. When we did not use JWT, when one would refresh the page, it would automatically logout. | 1 | We use the JWT to login automatically, once the user submits the login infomation, the JWT is generated and they can stay logged in to the website.
3 | We stored the password to the database, however, it is not secure if we do not encrypt the password and store to the database. | 2 | We use hash before store to the database.
Product | Profile Module
Date | 2017-09-16
Author | Sugarbois
Moderator | Rei Orikata
Inspectors | Timothy Poozhikala, Ronak Bharad
Recorder | Ivan Chan
Defect # | Description | Severity | How Corrected
1 | After clicking the edit the nickname button, it will show the textfield, however when we click the submit button to send the new nickname, it may send an empty nickname. | 3 | We prevent the case if the name is empty in client side.
2 | The profile was not able to retrieve the data from the database, even though the user was part of the database with all the details stored correctly. | 1 | We fixed the algorithm and the fetching of data by using different objects on just one profile.
Product | Write Question Module
Date | 2017-09-17
Author | Sugarbois
Moderator | Ivan Chan
Inspectors | Rei Orikata, Timothy Poozhikala
Recorder | Ronak Bharad
Defect # | Description | Severity | How Corrected
1 | After the question type is selected, the UI will show the answer for the specific type. It may show a UI for the wrong question type. | 1 | Give the if-statement to display the correct UI.
2 | When we try to add a question, the question would be added to the wrong category. | 1 | Provide a question type value and use an if-statement to store data to a specific category within the database.
3 | Before submitting the question, check if any of the values are empty, Otherwise it would send empty values. | 2 | Before submitting to the database, the program will filter the values to see if they are empty or not, and give a warning to the user.

## Unit Testing
Product | Multiple dropdown menu test 1.1
Date | 2017-09-15
Author | Sugarbois
Defect # | Description | Severity | How Corrected
1 | After clicking the button to initialize the dropdown menu, no menu was coming out of it. | 2 | Changed the code for the drop down menu to more clearly access the database of categories to pull from.
2 | After clicking the dropdown menu, not all of the categories displayed a sub-category | 2 | Planned a solution for recursively adding sub categories to the list of categories.
Product | Question Dialog Test 3.1
Date | 2017-09-17
Author | Sugarbois
Defect # | Description | Severity | How Corrected
1 | When the user would click the T/F question Option, then the Multiple Choice question option, the T/F would not dissapear and vice versa. | 2 | We rewrote the sections for the conditions of displaying the dialogs to writ ethe T/F and Multiple Chooice questions so one could not appear when the other was present.
Product | Submit Question Test 3.2
Date | 2017-09-17
Author | Sugarbois
Defect # | Description | Severity | How Corrected
1 | Clicking the Submit Question button would not actually send any data to the database. | 1 | Had to add pieces of code which would clearly send the data inputed to the database
2 | Clicking the Submit Question button would not submit it to the correct section of the database corresponding to its category. | 1 | Had to ensure that the sorting and organizing abilities of the database wore functioning and fix the category section to display the proper values.
Product | Category Select Test 3.3
Date | 2017-09-15
Author | Sugarbois
Defect # | Description | Severity | How Corrected
1 | After clicking the button to initialize the dropdown menu, no menu was coming out of it. | 2 | Changed the code for the drop down menu to more clearly access the database of categories to pull from.
2 | After clicking the dropdown menu, not all of the categories displayed a sub-category | 2 | Planned a solution for recursivley adding sub categories to the list of categories.
Product | Sign up account test 19.1
Date | 2017-09-16
Author | Sugarbois
Defect # | Description | Severity | How Corrected
1 | Selecting the sign-up for account button would not produce any result | 1 | Had to set up the page and connection to lead the user to a signup dialog when trying to sign up
2 | User data, after entered, would not be stored correctly in the database | 2 | Had to rewrite scripts calling database to ensure that the data being collected and sent over is correct and will store in the proper sections.
Product | Account already exist test 19.2
Date | 2017-09-16
Author | Sugarbois
Defect # | Description | Severity | How Corrected
1 | User data, after entered, would not be stored correctly in the database, thus after trying to sign in, multiple accounts of the same credentials were allowed | 3 | Made sure the database would store the information with the the proper tags and linking so that it could be cross-referenced properly.
Product | Log in test 19.3
Date | 2017-09-17
Author | Sugarbois
Defect # | Description | Severity | How Corrected
1 | The data previously entered to create the account was not properly stored within the database, so when the user would try to log in, it would not work. | 1 | Set up the proper database calls and organization to make sure the information is properly cross-referenced and selected.
Product | Help page 21.1
Date | 2017-09-20
Author | Sugarbois
Defect # | Description | Severity | How Corrected
1 | When the button was pressed to show the help page, we did not have a way to get rid of the dialog box | 2 | Recoded it to display on click and stop displaying on another click.